## CVE Ticket Tracker
[7 empty] | PT Privy Identitas Digital | [7 empty] | Nomor Formulir :
[7 empty] | Jl. Kemang Raya No. 15 C, Lantai 4, Bangka, Mampang Prapatan, Jakarta Selatan 12730 helpdesk@privy.id ¦ www.privy.id | [7 empty] | Revisi : 00
Tanggal :
[7 empty] | Logbook CVE Tracker Periode 2026 | [7 empty] | Dokumen Terbatas
No | Remediation Status |  | Description
1 | Pending |  | Perbaikan telah direncanakan atau sedang menunggu jadwal, namun pengerjaan belum dimulai.
2 | In Progress |  | Proses perbaikan (seperti patching atau konfigurasi ulang) sedang berjalan.
3 | Not Affected |  | Sistem setelah diperiksa terbukti tidak terdampak oleh celah keamanan tersebut.
4 | Not Applicable |  | Perbaikan tidak dapat diterapkan atau tidak relevan dengan arsitektur sistem saat ini.
5 | Completed |  | Proses perbaikan telah selesai dilakukan dan risiko telah dimitigasi sepenuhnya.
Notes |  | Aktivitas ini dilaksanakan apabila terdapat CVE yang ditemukan relevan dengan technology stack yang digunakan perusahaan
Ticket ID | CVE ID | CVE Reported Date | Severity | CVSS Score | Affected Asset/Product | Affected Version | Fixed Version | Asset Owner | Owner Email | Owner Team | Active Exploitation | Date Acknowledged by CTI Team | Remediation Date Plan | Remediation Status | Actual Remediation Date | Escalation Required | Comments/Notes | Risk Acceptance | Closure Date
Note on M15: Michael Dragon Muliawidjaja: Is the vulnerability actively use by Threat Actor in their exploitation? Active Exploitation -> Confirmed widespread use by threat actors (high priority) Limited Exploitation -> Spotted in isolated incidents or specific campaigns (medium priority) No Known Exploitation -> No current evidence of exploitation (low priority, monitoring status) Unknown/Under Investigation -> Insufficient intelligence data or analysis pending
Note on R15: Michael Dragon Muliawidjaja: When to mark "Yes": - Asset owner not responding after 2+ follow-ups - Remediation deadline will be missed without intervention - Asset owner requesting risk acceptance for Critical/High severity - Technical blockers preventing patching (vendor dependency, etc.)
Note on U15: Michael Dragon Muliawidjaja: The actual date when the CVE ticket was fully closed and no longer tracked

## DB
Active Exploitation | Risk Acceptance | Pending
Active Exploitation | Risk Avoidance | In Progress
Limited Exploitation | Risk Mitigation | Not Applicable
No Known Exploitation | Risk Transfer | Not Affected
Unknown/Under Investigation | No Risk (Not Affected) | Completed